## ARPA BVA
ARPA BVA - September 29, 2025
Description | Allocated | Obligated (thru PO/Contract, MOU) | Percent Obligated (deadline: 12/31/2024) | Amount Expended | Percent Expended (deadline: 12/31/2026) | Project Status
ARPA Consultants | 239313 | 239313 | 100% | 140287.03 | 58.62% | More Than 50% complete
ARPA- Administrative Support (FY24 - FY27) | 97223 | 97223 | 100% | 97223 | 100% | Complete
ARPA- Fire Dept-SCBA | 650000 | 650000 | 100% | 650000 | 100% | Complete
ARPA-United Way (CAN) | 1000000 | 1000000 | 100% | 344910.26 | 34.49% | Less than 50% complete
ARPA-Newhall Foundations | 1800000 | 1800000 | 100% | 604375 | 33.58% | Less than 50% complete
ARPA-Town of Hamden (Alliance for Trees) | 4990 | 4990 | 100% | 4990 | 100% | Complete
ARPA-Town Drainage Study | 199500 | 199500 | 100% | 42892.5 | 21.5% | Less than 50% complete
ARPA-Artist Outdoor Living Room | 2000 | 2000 | 100% | 2000 | 100% | Complete
ARPA-Village After School Program | 50000 | 50000 | 100% | 0 | 0% | Less than 50% complete
ARPA-Hamden Small Business Grant Program | 184794 | 184794 | 100% | 161911.66 | 87.62% | More Than 50% complete
ARPA-United Way (HPYC) | 165000 | 165000 | 100% | 57644.36 | 34.94% | Less than 50% complete
ARPA-Eligible Municipal Expenses | 13194665 | 13194665 | 100% | 13194665 | 100% | Complete
ARPA-Youth Mentorship Programs | 25000 | 25000 | 100% | 18336 | 73.34% | More Than 50% complete
ARPA-Community Outreach & Engagement - Six Lakes | 40000 | 40000 | 100% | 40000 | 100% | Complete
ARPA-Dept Public Works- Vehicles | 464206 | 464206 | 100% | 464206 | 100% | Complete
ARPA-Hamden Small Business Academy | 142500 | 142500 | 100% | 73542.45 | 51.61% | More Than 50% complete
ARPA - FY21 3.1 Public Safety Workforce | 5881147 | 5881147 | 100% | 5881147 | 100% | Complete
Total: | 24140338 | 24140338 | 100% | 21778130.26 | 90.21% | More Than 50% complete